| MPR for the month of May 2025 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| HADP-16: Alternate system of Agriculture for Sustainability |  |  |  |  |  |  |  |  |  |
|  |  |  | Target 2025-26 |  | Funds Received | Achievement 2025-26 |  |  | Bills in Treasury |  |
| S.N. | Activity Name | Phy. Unit | Phy. | Fin. | Fin. | Phy. |  | Fin. (lakhs) |  |  |
| 1 | Organic farming validation Cum incubation facility (one each in SKUAST-J&K) in existing facilities/ Bio-input strain identification / Production etc | No. of Units | 1 | 150 | 140 lakhs | - |  | - | - |  |
| 2 | Standardization/ Demonstration of Technologies in hand and in offing/ ITK etc in collaboration with APD & KVKs | No. of Demonstrations | 53 | 29 |  | OFRTS-South -07 North-04 |  | 1.5 | - |  |
| 3 | Capacity Building of Scientist and Officers and Hiring of Knowledge partners. | No. of Training | 13 | 11 |  | Department officers/ KVK Scientists trainings:02 |  | 3.00 | - |  |
| 4 | Incubation and Agri-startup fund for agriculture Technocrats/ Educated rural youth | No. of Startups | 10 | 50 |  | - |  | - | - |  |
| 5 | Workshops/ Seminar/ Exhibitions/ Conferences/ Mela/Goshti | Farmer Days | 2 | 10 |  |  |  |  | - |  |
| 6. | Contingencies/Salary |  | - | 30 |  |  |  | 4.50 | - |  |
|  | Total |  |  | 280 |  |  |  | 9.00 lakh |  |  |