| MPR for the month of March 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| HADP-16 |  | Alternate system of Agriculture for Sustainability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Target 2024-25 |  | Funds Received |  | Achievement 2024-25 |  |  | Work under process |  | %age of completion |  |  | Bills in Treasury |  |  |
| S.N. | Activity Name | Phy. Unit | Phy. | Fin. | Fin. |  | Phy. |  | Fin. (lakhs) |  |  |  |  |  |  |  |  |
| 1 | Organic farming validation Cum incubation facility (one each in SKUAST-J&K) in existing facilities/ Bio-input strain identification / Production etc | No. of Units | 1 | 217 | 320 lakhs |  | 1.Biopesticide Production Centre at MRCFC 2. Bio-input Production Centre |  | 130.00 | Biopesticide Production Centre Commissioned. Biofertilizers Production Unit likely to be commissioned upto May 2025 |  | 81%of the civil work has been completed |  |  | 2 |  |  |
| 2 | Standardization/ Demonstration of Technologies in hand and in offing/ ITK etc in collaboration with APD & KVKs | No. of Demonstrations | 53 | 20 |  |  | Bioanalysis Centre Commissioned 46 OFRTS |  | 4.00 | Research Papers, Review papers and Organic Manual under publication |  | 82% completed |  |  | 2 |  |  |
| 3 | Capacity Building of Scientist and Officers and Hiring of Knowledge partners. | No. of Training | 18 | 25 |  |  | Farmers Training: 12 Department officers/ KVK Scientists :05 Total : 17 |  | 19.00 | 17 trainings have been sanctioned for extension personals, department officers and practising farmers that are to be conducted |  | 99% |  |  | 1 |  |  |
| 4 | Incubation and Agri-startup fund for agriculture Technocrats/ Educated rural youth | No. of Startups | 10 | 100 |  |  |  |  | nil | 03 Agrithons planned (Central North and South Kashmir) |  | 30% |  |  | 0 |  |  |
| 5 | Workshops/ Seminar/ Exhibitions/ Conferences/ Mela/Goshtietc | Farmer Days | 4 | 13 |  |  | 1 brainstorming workshop conducted |  | 7.4 | 1 interaction workshop conducted, |  | 54% |  |  | 1 |  |  |
| 6. | Contingencies/Salary |  |  | 25 |  |  |  |  | 23.00 |  |  |  |  |  | 3 |  |  |
|  | Total |  |  |  |  |  |  |  | 183.4 lakh |  |  |  |  |  |  |  |  |