| Monthly Progress Report for February, 2025: Promotion of Year Round Mushroom Production (Project No 10) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S.No | Activity/Intervention | Physical Targets | Achievements | Work in Progress | Financial Target | Financial Achievement | Booked Expenditure/Bills in Treasury | Status of work/remarks |
| 1. | Research & Development |  | Technology transfer with respect to Enoki and King Oyster taken up with 04 entraprunners |  |  |  |  | 1)Data collected in fine tuning experiments with respect to Enoki and King Oyster under way. 2) Exotic strain Shimiji mushroom procured. 3)Elm Oyster and lions manne Mushroom Experiments Initiated 4)Apple Pruned wood collected from SKUAST campus and converted into Wood chips and wood saw dust for the preparation high value mushroom substrate. 5) Incubates of high value mushroom entraprunners conducted sale of 60 kg of enokii during Agritech mela on 22 -23rd Feb, 2025 at SKUAST-K. |
| 2. | Upgradation of Mushroom Research & Training Centre | 01 | -- | -- | 05 lakhs | -- | 05 lakhs | Civil work in progress |
| 3. | Purchases of Equipments and Machinery etc |  |  |  |  |  | 100 Lakhs |  |
| 4. | Hiring of services | 07 | - | - | 08 Lakhs | -- | 5.5 lakhs | 07 positions filled |
| 5. | Last Year liability | - | - | - | - | - | 08 Lakhs |  |

Sd/

Prof. Shaheen Kousar Jan

PI, HADP Project No 10

Few Snippets of Work Done