| Monthly Progress Report for March, 2025: Promotion of Year Round Mushroom Production (Project No 10) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S.No | Activity/Intervention | Physical Targets | Achievements | Work in Progress | Financial Target | Financial Achievement | Booked Expenditure/Bills in Treasury | Status of work/remarks |
| 1. | Research & Development |  | Technology transfer with respect to Enoki and King Oyster taken up with 04 entraprunners |  |  |  |  | 1)Data collected in fine tuning experiments with respect to Enoki and King Oyster under way. 2) Exotic strain Shimiji mushroom procured. 3)Elm Oyster and lions manne Mushroom Experiments Initiated 4)Apple Pruned wood collected from SKUAST campus and converted into Wood chips and wood saw dust for the preparation high value mushroom substrate. 5) Incubates of high value mushroom entraprunners have processed the base material for high value mushroom at SKUAST-K. 6) Spawn production of Elm and Shimiji mushroom initiated. |
| 2. | Purchases of Equipments and Machinery etc |  |  |  |  |  | 106.0 Lakhs |  |
| 3. | Hiring of services | 07 | - | - | - | -- | 8.0 Lakhs | 07 positions filled |
| 4. | Capacity Building | 02 Training programmes |  |  |  |  | 04 Lakhs |  |
|  | Total Expenditure in the Year 2024-25 |  |  |  |  |  | 118.0 Lakh |  |

*Outstanding Liability (un paid bills) of 17.50 lakh to be paid out of budget 2025-26

Sd/

Prof. Shaheen Kousar Jan

PI, HADP Project No 10

Few Snippets of Work Done