Sher-e-Kashmir

University of Agricultural Sciences and Technology of Kashmir

MOUNTAINRESEARCHCENTREFORFIELDCROPS

Khudwani-Kulgam 192102

Director,

DOAP&FW,

Jammu

No.Au/MRCFC/Estt./HADP/

Dated:  30-06-2025

Subject:	Submission of Physical and Financial Progress Report under HADP project No.11 “Promotion of Oilseeds”

Sir,

Kindly find enclosed monthly progress report of the HADP project No. 11 “Promotion of Oilseeds” for the month of June, 2025 for favour of information and further necessary action at your end please.

Yours faithfully,

(Dr. Najeeb-ul-Rehman Sofi) Associate Director Research & PI HADPProjectNo.11

Copy for information

Director Research SKUAST-K, Shalimar

| Monthly progress report for June,2025 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| S. No | Activity / Intervention | Physical targets | Achievements | Work in progress | Financial target | Financial achievement | Bills in treasury | Status of work/ remarks |
| 1. | Site Specific Demonstrations | 200 | - Compilation of data from farmers’ fields with respect 200 Site Specific demonstrations on high yielding Brown Sarson variety (Shalimar Sarson-2) and Gypsum got completed across the valley by scientists of the Station and Extension Agencies of Department of Agriculture & KVKs. Recording comparative performance of the new variety in comparison to farmers variety is under progress. - Compilation of minikit trials on two newly developed varieties KBS-63 & KBS-100 at 32 locations across eight districts of the valley in collaboration with officials of Department of Agriculture Kashmir. Data analysis is under progress. |  |  |  |  |  |
| 2. | Seed Production |  | Harvesting of Nucleus seed of released varieties of Shalimar Sarson-1, 2 & 3 and Shalimar Gobhi Sarson-1. Also harvesting/threshing of breeder seed plots of Shalimar Sarson-2 was successfully done. |  |  |  |  |  |
| 3. | Progress of Mustard Oil Filter Press |  | Extraction of Shalimar sarson-2 oil through Mustard Oil Filter Press established at Khudwani centre of SKUAST-K is functional on customer hiring basis. Launch of Shalimar Sarson oil brand by Hon’ble Lieutenant Governor of J&K on 14th June 2025. |  |  |  |  |  |
| 4. | Research activities |  | - The following research trials were successfully harvested/threshed and post harvest data under progress: - IVT Mustard(B.juncea) - MLT Mustard(B.juncea) - AVT Gobhi Sarson - IVT Gobhi Sarson - IVT B. rapa - AVT B. rapa - Evaluation of germplasm: - Brassica rapa : 50 genotypes - Brassica napus: 50 genotypes |  |  |  |  |  |