Sher-e-Kashmir

University of Agricultural Sciences and Technology of Kashmir

MOUNTAINRESEARCHCENTREFORFIELDCROPS

Khudwani-Kulgam 192102

Director,

DOAP&FW,

Jammu

No.Au/MRCFC/Estt./HADP/1070-71

Dated:  29-07-2025

Subject:	Submission of Physical and Financial Progress Report under HADP project No.11 “Promotion of Oilseeds”

Sir,

Kindly find enclosed monthly progress report of the HADP project No. 11 “Promotion of Oilseeds” for the month of July, 2025 for favour of information and further necessary action at your end please.

Yours faithfully,

(Dr. Najeeb-ul-Rehman Sofi) Associate Director Research & PI HADPProjectNo.11

Copy for information

Director Research SKUAST-K, Shalimar

| Monthly progress report for July,2025 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| S. No | Activity / Intervention | Physical targets | Achievements | Work in progress | Financial target | Financial achievement | Bills in treasury | Status of work/ remarks |
| 1. | Site Specific Demonstrations | 200 | - The centre successfully conducted 200 site specific demonstrations during rabi 2024-2025 in which Shalimar Sarson 2 (SS2)was demonstrated in comparison to farmers varieties/ old varieties. The results revealed that SS2 recorded a high yield potential ranging from 13-17 q/ha in comparison to 10.5-14.0 q/ha recorded by old / farmers varieties. The farmers have shown great interest in SS2 and are replacing their traditional/old varieties with SS2 in future. This will greatly increase the Seed replacement and varietal replacement rate in oilseed, thereby increasing production & productivity of the crop. - Compilation of data of minikit trials received from Department of Agriculture on two newly developed varieties KBS-63 & KBS-100 at 32 locations across eight districts of the valley in collaboration with officials of Department of Agriculture Kashmir is under progress. |  | 30.0 | 4.63 | 3.7 |  |
| 2. | Seed Production |  | - Processing of Breeder/Foundation seed of oilseed(brown sarson) produced during rabi 2024-2025 is under progress. |  |  |  |  |  |
| 3. | Progress of Mustard Oil Filter Press |  | Extraction of Shalimar sarson-2 oil through Mustard Oil Filter Press established at Khudwani centre of SKUAST-K is functional on customer hiring basis. |  |  |  |  |  |
| 4. | Research activities |  | - Trials on Kharif oilseed crop(soybean) at Dryland Agriculture Research Station, SKUAST-Kashmir is under progress. - Sowing of Kharif oilseed(sunflower) trials on 14.7.2025 & 28-7-2025 done at MRCFC Khudwani SKUAST-K - DUS Characterization of newly developed varieties completed and DNA fingerprinting is under progress. - Draft proposal for release of KBS63 is under progress and will be presented in the forthcoming UV RC - Upgraded package of practices for brown sarson cultivation in English and Urdu prepared. |  |  |  |  |  |