Sher-e-Kashmir

University of Agricultural Sciences and Technology of Kashmir

MOUNTAINRESEARCHCENTREFORFIELDCROPS

Khudwani-Kulgam 192102

Director,

DOAP&FW,

Jammu

No.Au/MRCFC/Estt./HADP

Dated: 29-08-2025

Subject:	Submission of Physical and Financial Progress Report under HADP project No.11 “Promotion of Oilseeds”

Sir,

Kindly find enclosed monthly progress report of the HADP project No. 11 “Promotion of Oilseeds” for the month of August, 2025 for favour of information and further necessary action at your end please.

Yoursfaithfully,

(Dr.Najeeb-ul-RehmanSofi) AssociateDirectorResearch&PIHADPProjectNo.11

Copy for information

Director Research SKUAST-K, Shalimar

| Monthly progress report for August,2025 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| S. No | Activity/ Intervention | Physical targets | Achievements | Work in progress | Financial target | Financial achievement | Bills in treasury | Status of Work / remark |
| 1. | Extension activities & varietal development programme |  | - Packing of the seed material for laying minikit trials of newly developed variety KBS-100 in 8 districts of the valley. - Preparation of release proposals for the newly developed variety KBS-63 alongwith package of practices which has completed all technical formalities for release. - Upgraded package of practices for brown sarson cultivation in English and Urdu prepared. |  | 30.0 (Released=15.0) | 3.87 | 4.55 |  |
| 2. | Seed Production |  | - Processing of Breeder/Foundation seed of oilseed(brown sarson) produced during rabi 2024-2025 is completed & ready for dispatch as per the indent. |  |  |  |  |  |
| 3. | Progress of Mustard Oil Filter Press |  | Extraction of Shalimar sarson-2 oil through Mustard Oil Filter Press established at Khudwani centre of SKUAST-K is functional on customer hiring basis. |  |  |  |  |  |
| 4. | Research activities |  | - Evaluation of sunflower genotypes for various Agro-morphological traits. - Evaluation of eight groundnut lines received from BARC for various morphological traits. - Trials on Kharif oilseed crop(soybean) at Dryland Agriculture Research Station, SKUAST-Kashmir is under progress. - DUS Characterization of newly developed varieties completed and DNA fingerprinting is under progress. |  |  |  |  |  |