Sher-e-Kashmir

University of Agricultural Sciences and Technology of Kashmir

MOUNTAINRESEARCHCENTREFORFIELDCROPS

Khudwani-Kulgam 192102

iq

Director,

DOAP&FW,

Jammu

No.Au/MRCFC/Estt./HADP/

Dated: 30-09-2025

Subject:	Submission of Physical and Financial Progress Report under HADP project No.11 “Promotion of Oilseeds”

Sir,

Kindly find enclosed monthly progress report of the HADP project No. 11 “Promotion of Oilseeds” for the month of September, 2025 for favour of information and further necessary action at your end please.

Yoursfaithfully,

(Dr.Najeeb-ul-RehmanSofi) AssociateDirectorResearch&PIHADPProjectNo.11

Copy for information

Director Research SKUAST-K, Shalimar

| Monthly progress report for September,2025 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| S. No | Activity/ Intervention | Physical targets | Achievements | Work in progress | Financial target | Expenditure/Released | Booked/Bills in treasury | Total |
| 1. | Extension activities & varietal development programme |  | - Supply of seed material for laying minikit trials of newly developed variety KBS-100 in 8 districts of the valley. - Visit of Principal Secretary(Agri)/ Additional Chief Secretary to the centre and reviewed the oilseed and other field crops of the centre. - Two farmer training programmes entitled “Best Management Practices for Improving Oilseed Productivity and Quality” each at Kulgam and Anantnag District were successfully conducted under HADP No11 - Mid term review of oilseed was presented and was highly acknowledged by the reviewing team. |  | 30.0 (Released=15.0) | 8.72/4.05 | 4.67/3.0 | 11.72 |
| 2. | Seed Production |  | - The inspection of Breeder/Foundation seed of oilseed(brown sarson) produced during rabi 2024-2025 is completed by the certifying agency and tags were allotted to processed seed. - The seed is ready for dispatch to Deptt of Agri. Kashmir as well as Deptt. of Agri. Jammu |  |  |  |  |  |
| 3. | Progress of Mustard Oil Filter Press |  | Extraction of Shalimar sarson-2 oil through Mustard Oil Filter Press established at Khudwani centre of SKUAST-K is functional on customer hiring basis. |  |  |  |  |  |
| 4. | Research activities |  | 1.DNA finger printing of released varieties of Brown sarson has been completed 2. Seed material for laying the Rabi Trials of oilseed crop has been sorted and kept ready for sowing |  |  |  |  |  |