Sher-e-Kashmir

University of Agricultural Sciences and Technology of Kashmir

MOUNTAINRESEARCHCENTREFORFIELDCROPS

Khudwani-Kulgam 192102

iq

Director,

DOAP&FW,

Jammu

No.Au/MRCFC/Estt./HADP/

Dated: 30-09-2025

Subject:	Submission of Physical and Financial Progress Report under HADP project No.11 “Promotion of Oilseeds”

Sir,

Kindly find enclosed monthly progress report of the HADP project No. 11 “Promotion of Oilseeds” for the month of October,2025 for favour of information and further necessary action at your end please.

Yoursfaithfully,

(Dr.Najeeb-ul-RehmanSofi) AssociateDirectorResearch&PIHADPProjectNo.11

Copy for information

Director Research SKUAST-K, Shalimar

| Monthly progress report for October,2025 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| S. No | Activity/ Intervention | Physical targets | Achievements | Work in progress | Financial target | Expenditure/Released | Booked/Bills in treasury | Total |
| 1. | Extension activities & varietal development programme |  | - Three farmer training programmes entitled “Best Management Practices for Improving Oilseed Productivity and Quality” each at Anantnag, Pulwama and Kulgam Districts were successfully conducted under HADP No11 |  | 30.0 (Released=15.0) | 8.72/4.05 | 4.67/3.0 | 11.72 |
| 2. | Seed Production |  | - Breeder seed production of Shalimar sarson 2 was taken on area of 0.5 ha at MCFC,Khudwani during Rabi 2025-26 - Foundation seed production of Shalimar sarson 2 was taken on area of 6.0 ha at MCFC,Khudwani during Rabi 2025-26 - Dispatched 2 q of breeder seed of SS2 to Deptt of Agri. Kashmir through NSP Seeds Shalimar in first week of October for production of foundation seed . - Dispatched 20 q of foundation seed of SS2 to Deptt of Agri. Kashmir through NSP Seeds Shalimar in first week of October for production of foundation/ certified seed - Production of Breeder seed of Pre Release variety of Brown Sarson (KBS 63) at KVK, Anantnag and KVK, Pulwama on an area of 3 kanal at each location. |  |  |  |  |  |
| 3. | Progress of Mustard Oil Filter Press |  | Extraction of Shalimar sarson-2 oil through Mustard Oil Filter Press established at Khudwani centre of SKUAST-K is functional on customer hiring basis. |  |  |  |  |  |
| 4. | Research activities |  | - IVT Gobhi sarson with 12 treatments - IVT Brown sarson with with 12 treatments - AVT Brown sarson with 8 entries - IVT brassica juncea with 10 treatments - Maitenance of Brown sarson and Gobhisarson germplasm lines |  |  |  |  |  |