Sher-e-Kashmir

University of Agricultural Sciences and Technology of Kashmir

MOUNTAINRESEARCHCENTREFORFIELDCROPS

Khudwani-Kulgam 192102

Sher-e-Kashmir

University of Agricultural Sciences and Technology of Kashmir

MOUNTAINRESEARCHCENTREFORFIELDCROPS

Khudwani-Kulgam 192102

iq

Director,

DOAP&FW,

Jammu

No.Au/MRCFC/Estt./HADP/2122-23

Dated: 29-11-2025

Subject:	Submission of Physical and Financial Progress Report under HADP project No.11 “Promotion of Oilseeds”

Sir,

Kindly find enclosed monthly progress report of the HADP project No. 11 “Promotion of Oilseeds” for the month of November,2025 for favour of information and further necessary action at your end please.

Yoursfaithfully,

(Dr.Najeeb-ul-RehmanSofi) AssociateDirectorResearch&PIHADPProjectNo.11

Copy for information

Director Research SKUAST-K, Shalimar

| Monthly progress report for November,2025 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| S. No | Activity/ Intervention | Physical targets | Achievements | Work in progress | Financial target | Expenditure | Booked/Bills in treasury | Total |
| 1. | Capacity building programme |  | - Two farmer training programmes (50 farmers each) entitled “Best Management Practices for Improving Oilseed Productivity and Quality” were successfully conducted at Anantnag & Budgam Districts. - One training programme(60 participants) to officials of line department & SKUAST-K entitled “untie the yield complexities in oilseed crops…” was successfully conducted at MRCFC, Khudwani. |  | 30.0 (Released=25.5) | 9.0 | 3.95 | 12.95 |
| 2. | Seed Production |  | - Breeder seed production of Shalimar sarson 2 taken on area of 0.5 ha at MCFC,Khudwani for Rabi 2025-26 is showing good stand. - Foundation seed production of Shalimar sarson 2 taken on area of 6.0 ha at MCFC,Khudwani during Rabi 2025-26 is showing good crop stand. |  |  |  |  |  |
| 3. | Progress of Mustard Oil Filter Press |  | Extraction of Shalimar sarson-2 oil through Mustard Oil Filter Press established at Khudwani centre of SKUAST-K is functional on customer hiring basis. |  |  |  |  |  |
| 4. | Research activities |  | - IVT Gobhi sarson with 12 treatments laid at Khudwani is under progress. - IVT Brown sarson with with 12 treatments laid at Khudwani is under progress - AVT Brown sarson with 8 entries laid at Khudwani is under progress. - IVT Brassica juncea(mustard) with 10 treatments laid at Khudwani is under progress. - Maintenance of Brown sarson and Gobhi sarson germplasm lines laid at Khudwani is under progress. - Thinning and cleaning operations completed. |  |  |  |  |  |
| 5. | Varietal development |  | One variety KBS63 recommended by pre-UVRC for release. Minikit trials of one more variety KBS100 for 2nd year evaluation for in all 10 districts of Kashmir are under progress. |  |  |  |  |  |