| S.No |  | Monthly Progress Report HADP Project No. 02 Promotion of Niche crops in UT of J&K |  |  |  |  | MPR December, 2025 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Project Code No. | Activity |  | Phy Unit | Target 2025-26 |  | Funds received (Lakhs) |  |  | Work under progress | % of Completion |
|  |  |  |  |  | Phy. | Fin. | Fin. | Phy. Ach. | Fin.Ach. |  |  |
| 1 | P02NC33H40/35 P02NCH35 | Collection, evaluation and conservation of germplasm and development of markers of Niche crops (Saffron, Kalazeera, Mushkbudji, Red Rice and Chilli) |  | No. of collections | 50 new collections for five (Niche Crops) | 100.00 | 85.00 | 50 Accessions of (05) Niche crops collected | 40.00 | A total of 162 number of accessions were collected & are under evaluation for varietal development | 50 |
| 2 |  | Standardization of Production Technology of Niche crops and their demonstration (Saffron, Kalazeera, Mushkbudji, Red Rice and Chilli) |  | No. of trials | 05(Niche Crops) |  |  | 05 research trails laid and are under evaluation |  | Field trial on Saffron, Kalazeera &Shallot are under evaluation for yield and yield attributes | 55 |
| 3 |  | Devising Package of Practices for Shallot |  | No. of trials | 01 (Shallot) |  |  | Field trial on Shallot laid during this season |  | Trails under evaluation for bulb-to-bulk production for validation and confirmation of the results | 55 |
| 4 |  | Conduct of OFT’s on Shallot |  | No. of OFTs | 20 No |  |  | Twenty (20) OFTs conducted |  | Shallot planting material were distributed among FPC for production of quality planting material | 100- |
| 5 | P02NCH26/27 | Establishment of processing and handling unit for Mushkbudji |  | No. of Units | 01 No |  |  | One Unit established | 5.00 | Established | 100 |
| 6 |  | Modern Rice Mill for Mushkbudji |  |  | 01 No |  |  | 01 unit Installed |  | Installed | 100 |
| 7 | P02NCH28/29 | Establishment of processing and handling unit for Red Rice |  | No. of Units | 01 No |  |  | One Unit established | 10.00 | Established | 100 |
| 8 |  | Modern Rice Mill for Red Rice |  |  | 01 No |  |  | 01 unit Installed | - | Installed | 100 |
| 9 | P02NCH21 | Establishment of processing and handling unit for Chilli along with equipment’s |  | No. of Units | 01 No |  |  | Under process | 5.00 | Processing unit established & procurement of equipment and machinery completed. | 65 |
| 11 | P02NCH30,31,32,35,37 &38 | Trainings/ HRD |  | No. of Trainings | 16 No |  |  | Eight (08) training programmes conducted involving 320 farmers | 1.00 | The remaining (08) training programmes shall be conducted during Jan -February, 2026 | 50 |
|  |  |  | Total |  |  |  |  |  | 61.00 |  |  |

Note: Rs 85.00 lakhs (Ist& 2ndInstalment) was released for HADP Project No.02 and expenditure to the tune of Rs 61.00 lakh was made upto 30th

Principal Investigator

HADP Project No.2

December 2025.