| MPR for the month of September 2025 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| HADP-13 |  | ADOPTION AND PROMOTION OF INTEGRATED FARMING SYSTEM (IFS)/INTEGRATED LIVELIHOOD SYSTEM (ILS) in UT of J&K |  |  |  |  |  |  |  |  |
|  |  |  | Target 2025-26 |  | Funds Received | Achievement 2025-26 |  | Work under process | %age of completion | Bills in Treasury |
| S.N. | Activity Name | Phy. Unit | Phy. | Fin. | Fin. | Phy. | Fin. (Lakh) |  |  |  |
| 1 | Centre of Excellence on Integrated Farming System | No. of Units | 1 | 45.00 | 40.00 lakhs | - Plantation of mulberry plants along the boundary of IFS model - Upgradation of Fish pond cum duckery unit - Repairement and renovation of existing six polyhouses and one green house inside IFS unit - Crop Diversification | 22.370 | IFS model and centre of excellence at FoA, Wadura under process | 55 %of the work has been completed | An amount of Rs. 15.70 Lakhs has been submitted in treasury in the month of September |
| 2 | Standardization and demonstration of IFS units/District | No. of Demonstrations | 100 | 10.00 |  | 50 |  | - | - |  |
| 3 | Capacity Building of Scientist and Officers, Hiring of Knowledge partners, seminar/ workshops etc | No. of Training& workshop | 4 farmers training and 3 Line deptt./KVK training | 5.00 |  | 1 |  | - | - |  |
| 6. | Contingencies |  |  | 20.00 |  |  |  |  |  |  |
|  | Total |  |  | 80.00 lakhs |  |  |  |  |  |  |