Monthly progress Report January                                                                                                          Project No. 03 Promotion of Vegetables/ Exotic Vegetables

| S. No | Activity | Physical Target 5 YEAR (J&K) | Physical Target 2024-25 (J&K) | Achievement 2024-25 | Cumulative Achievement | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 01. | Identification of best suited area specific vegetable crops & Development of Improved Vegetable Varieties. |  |  |  |  |  |
|  | A) Conduct of OFT’s | 100 | 20 | 20 | 40 | 20 on farm trials successfully conducted |
| 02. | Design and manufacturing of new and improved region-specific Hi-Tech structures. |  |  |  |  |  |
|  | Development/refinement of package of practices under protected conditions. (Crops kharif: Tomato, Capsicum, Cucumber (Target for year 2025-26) (Crops rabi: Lettuce, Spinach, Coriander, Methi, Pea, Kale, Knol-khol). | 10 crops | 10 crops | 10 crops | 10 crops | Trials laid out and evaluation going on |
|  | Development/refinement of package of practices under organic/ Natural farming systems. Crops: Chilli, Okra, Onion, Knol-khol, Kale, Sprouting Broccoli, Cabbage, Cauliflower, Pea. | 10 crops | 10 crops | 10 crops | 10 crops | Trials laid out and evaluation going on |

*Note: Rs 68.00 (1st Instalment& 2nd Instalment) were released for Project No 03 and expenditure to the tune of Rs.85.00 (Lakh) was made/Booked till end January 2025.