Monthly Progress Report for July,2025 HADP 03 Project: Promotion of Vegetables/ Exotic Vegetables

| S. No. | Activity Code | Activity | Physical Target | Booked Expenditure(₹ in lakh) | Total Expenditure (₹ in lakh) | Achievements |
| --- | --- | --- | --- | --- | --- | --- |
| 01 | P03EXV01 | Identification of best suited area-specific vegetable crops & development of improved vegetable varieties. |  | 5.47 | 0.00 |  |
|  |  | - On-Farm Trials (OFTs) | 20 OFTs |  |  | OFTs ongoing |
|  |  | - Varietal/ Hybrid Development | 10 Crops |  |  | 2 varieties released (SKC-1) & (SH-BH-3). Varietal development in other vegetable crops going on. |
| 02 | P03EXV02 | Design & manufacturing of new and improved region-specific Hi-Tech structures |  |  |  |  |
|  |  | - Protected cultivation: Package of practices: (Crops kharif: Tomato, Capsicum, Cucumber) (Crops rabi: Lettuce, Spinach, Swiss Chard, Coriander, Methi, Kale, Knol-khol) | 10 Crops |  |  | Ongoing |
|  |  | - Natural farming: Package of practices: (Tomato, brinjal, chilli, capsicum, cabbage, broccoli, knol khol, radish, carrot, turnip). | 10 Crops |  |  | Ongoing |

Totalexpenditure 17.00 lah as pending claims for the yaer 2024-2025